Demonstrating the Capabilities of the UtilityNetwork ADE
Work roadmap

---
Overview
- The UtilityNetwork ADE is enormously complex and has many advantages.
- However, most of these advantages are still only theoretically defined.
- It would take much more than 6 months of work and a couple open data sets to demonstrate all of them.
- We should focus on a few important ones, which will also allow for the research to grow.

---
Overview
- The chosen advantages should be expressed generally, to demonstrate the flexibility of the data model.
- This means not getting too bogged down in network specifics.
  - More intricate and network-specific applications can be better developed once general experience has been gained.
- The advantages should be expressed in as a simple sample as possible to reduce complexity & allow for easy reproducibility & expandability.

---
Overview
- Advantages of the UtilityNetwork ADE
  - Model different network types in a single ecosystem.
  - Maintain explicit separation between topography & topology.
  - Representation in RDBMS (3DCityDB), use of pgRouting for performing routing analysis
  - Model functional characteristics of network operation.
  - Model dependencies of different networks on each other.
- This thesis will demonstrate application of all of these advantages.

---
Goal of Thesis
- The goal of this thesis is to create a CityGML dataset, extended with UtilityNetwork ADE that models a subset of the water and electrical network in Nanaimo, containing the Reservoir #1 Energy Reclamation Facility and a nearby suburb.
- Furthermore, a basic simulation shall be created that will demonstrate fluctuations in the electrical network caused by changes in the water network.
- Time permitting, the simulation will be expanded to allow for hypothetical addition of photovoltaic panels on houses to see how the simulation changes (this is for a total blue-sky scenario).

---
Goal of Thesis
- It is important to note that this thesis is intended to test & demonstrate the functional advantages of the UtilityNetwork ADE, not necessarily to create a highly accurate network dynamic model.
- A secondary goal of this thesis is also to identify areas of potential improvement & refinement for the UtilityNetwork ADE development team.

---
Goal #1: Model Different Network Types in a Single Ecosystem
- The Nanaimo water pipe network dataset from the Nanaimo Open Data Catalogue will be used as the basis of the water network.
- We have PDFs of more detailed water network info around the Reservoir #1 facility.
- Bill Sims has mentioned that he could give us a contact that can give us electric infrastructure data, but we do not have it yet. In absence, we can just use the street network as a surrogate.
- He also mentioned that he could give us single-line diagrams of the cables around the facility, but we will have to wait and see on that.

---
Goal #1: Model Different Network Types in a Single Ecosystem
Task	Expected Completion Date
Create basic water network (pipes & house endpoints only)	Done
Add appurtenances to water network	Currently in progress, finish by 2018-04-02
Create electric network (will already have appurtenance experience from water network)	2018-04-16 (two weeks)

---
Goal #2: Create Explicitly-Defined Topological Representation
- This is intended to demonstrate how easily a user could switch between topographical and topological views when using the UtilityNetwork ADE
- Will have to be done manually, but the subset is small enough to be feasible.

---
Goal #2: Create Explicitly-Defined Topological Representation
Task	Expected Completion Date
Clone the source data for water & electric networks & manually edit them to make a topological representation of themselves.	Done
Add appurtenances to water network	Currently in progress, finish by 2018-04-02
Create electric network (will already have appurtenance experience from water network)	2018-04-16
Clone the source data for water & electric networks & manually edit them to make a topological representation.	2018-04-23 (two weeks)
Modify the FME transformer to use the topological data for the topological elements, instead of just duplicating the topographical representation.	2018-05-07 (two weeks)

---
Goal #3: Insert all Network Features into 3DCityDB
- Having the network features in the 3DCityDB will allow for pgRouting to be used to perform functional connectivity & routing analysis.
- Giorgio’s functions have already proved quite useful in this regard.
- A Python script (with psycopg2) can be used to convert the CityGML file to Postgres (+PostGIS & 3DCityDB)
- It can also be done with FME, but Python is preferable due to being open source.

---
Goal #3: Represent Network System in 3DCityDB
Task	Expected Completion Date
Clone the source data for water & electric networks & manually edit them to make a topological representation of themselves.	Done
Add appurtenances to water network	Currently in progress, finish by 2018-04-02
Create electric network (will already have appurtenance experience from water network)	2018-04-16
Clone the source data for water & electric networks & manually edit them to make a topological representation.	2018-04-23
Modify the FME transformer to use the topological data for the topological elements, instead of just duplicating the topographical representation.	2018-05-07
Create Python script that uses Giorgio’s functions to insert the network features into 3DCityDB (already have some exploratory experience here).	2018-05-21 (two weeks)
Begin to develop a set of Python functions to perform valuable operations to interact with the network using pgRouting (get element by gmlid, route all terminal elements back to source, change status of valve element from open to closed & vice versa, etc.). This work will be continued in milestone 2.	2018-06-18 (one week) Note: it is only beginning to develop the functions (not a “real” deadline)

---
Milestone 1
- Milestone 1 is marked by the networks being totally finished. There should be no more work on creating the networks (barring emergencies, of course).
- We will be able to use Python to (at least):
  - Retrieve information about elements in the networks.
  - Change the properties of elements in the networks.
  - Perform basic routing analysis & selectively remove elements from the networks (breakage simulation).
- A presentation will also be delivered to Dr. Günther-Diringer and possibly the UtilityNetwork ADE working group.

---
Goal #4: Model functional Characteristics of Network Operation
- The pgRouting library will be used to perform network routing analysis necessary to model network functionality:
  - Connectivity checks (exclude elements that have been disconnected due to breakage)
  - Circuit algebra (for electric network)
- Lay out in clear terms the meaning of network elements and how they are to be treated when routing.
  - Turbines will be members of water & electric network
  - Exclude valves when they are set to “closed”.
  - Exlcude elements when they are “outOfService” (broken).
  - Terminal elements (houses) route back to the Reservoir. element
  - Etc...

---
Goal #4: Model functional Characteristics of Network Operation
Task	Expected Completion Date
Continue the work from milestone 1 – finalize functions that interact with network to open/close valves based on input, calculate demand from houses & remove from sources, etc.	2018-07-02 (two weeks)

---
Goal #5: Model Dependency of Electric Network on Water Network
- With the networks finished and in the database, we can build a system that involves the water and electrical network, wherein the electrical network is dependent on the water network.
- A Python class will be developed that will step through time steps and modify the network depending on the inputs, as well as summarize results in final tables.

---
Goal #5: Model Dependency of Electric Network on Water Network
- It will involve two types of “production” of media in a network:
  - Explicit (a network element produces an amount of medium defined by a value at that time step)
  - Implicit (a network element produces an amount of medium defined by values of other elements in the network.
- For example:
  - The water leading into the reservoir facility is explicit, as it is defined by input data.
  - The electricity leading out of the facility is implicit, as it is defined by the amount of water coming into the facility.

---
Goal #5: Model Dependency of Electric Network on Water Network
Read the current in flow rate at the meter (IF) in the reservoir facility. Set the valve elements (Va, Vb, Vc) to open or closed in the database, accordingly.

---
Goal #5: Model Dependency of Electric Network on Water Network
Increment the current water level increment in the reservoir (R) by (flow rate * time). If the resulting value exceeds the maximum capacity, just set it to max (excess water gets flushed).

---
Goal #5: Model Dependency of Electric Network on Water Network
Perform a connectivity check by attempting to route each turbine (Ta, Tb, Tc) to the meter (IF) along the water network. For those that succeed, increment their power supplied by a function involving the turbine parameters and (flow rate * time). This basically makes it so turbines with closed valves generate 0 power.

---
Goal #4: Model Dependency of Electric Network on Water Network
Perform a connectivity check for all the houses to the reservoir along the water network. For those that succeed, sum their demand at that time step and subtract that value from the reservoir’s level. If this makes the reservoir water level go negative, set it to 0 and log this in a summary table (in real life, additional water will be provided directly from the water treatment plant, bypassing the facility).

---
Goal #5: Model Dependency of Electric Network on Water Network
For each house, route it back to every electrical generation device it can find (turbines, Ta, Tb, Tc). Use circuit algebra to figure out exactly how much power to remove from each generation device based on the house’s demand at that time step. If there ends up being a net deficit, log it in a summary table (in real life, the difference would be made up for by the rest of the grid).

---
Goal #5: Model Dependency of Electric Network on Water Network
- This will demonstrate a simple network simulation of an electrical network that is coupled with the water network.
- Adjusting the water flow via the input data tables will cause automatic responses in the electrical output.
- The way pgRouting works (accepting a query to build the routing table) allows for elements to be excluded via their properties.
  - Valves to be excluded because they are closed
  - Specific elements to be removed to simulate breakages.

---
Goal #5: Model functional Characteristics of Network Operation
Task	Expected Completion Date
Continue the work from milestone 1 – finalize functions that interact with network to open/close valves based on input, calculate demand from houses & remove from sources, etc.	2018-07-02
Implement all the functions developed in the python class in a single process (using steps previously outlined)	2018-07-23 (three weeks)
Testing & refinement	2018-07-30 (one week)
If time permits: develop a basic GUI to allow for interactive input of element breaks & stepping through the simulation interactively.	2018-07-30 (???)

---
Milestone 2
- Milestone 2 is marked by the network coupling demonstrated via a simple time-based simulation. Modifying the input water parameters will cause differences in the electricity delivered.
- Optimally, other parameters can be specified (breakages, change turbine parameters, etc.)
- Remainder of the time will be devoted to finalizing the thesis final report & presentation.